## Sheet1
Masters Travel Service - Sustainability ACTION plan 2025 - 2027
| SUBJECT | OBJECTIVE | ACTION | MONITORING | OUTCOME | START DATE | DEADLINE | STATUS | FINANCE | RESULTS | COMMENTS
[9 empty] | (add end of action plan) | (add end of action plan)
1 | Sustainable Development Management and Legal Compliance | 1. Appoint a dedicated Sustainability Coordinator. | take Travelife training and exams. | Sustainability Team | Achieve full compliance with sustainability management practices and legal frameworks. | 2024-07-01 | 2025-01-01 | COMPLETE
2 |  | 2. Organize a 'Green Team' to oversee sustainability impacts. | Select key personnel and management | Sustainability Team | Support governance and oversight of sustainability measures. | 2024-11-01 | 2025-03-01 | COMPLETE |  |  | Staff training programs, communication platforms.
3 |  | 3. Develop and communicate the company’s sustainability mission and vision. | Send Sustainability policy to upload on group website. | Sustainability Team | Enhance stakeholder awareness of sustainability commitments. | 2024-11-01 | 2025-12-01 | COMPLETE |  |  | Sustainability Policy uploaded to the website.
4 |  | 4. Conduct an initial sustainability baseline assessment. | Follow Travelife platform requirements and instructions. | Sustainability Team | Establish baseline data for sustainability performance. | 2025-02-01 | 2025-03-01 | COMPLETE
5 |  | 5. Establish a sustainability evaluation system for suppliers. | create using resources from Travelife. Monitor and use for all excursion suppliers renewal. Complete the hotel monitoring spreadsheet at the start of each year. | Sustainability Team | Ensure supplier alignment with sustainability goals. | 2024-09-01 | 2025-06-01 |  |  |  | Spreadsheet monitoring system and appraisal tool in place.
6 |  | 6. Publish annual sustainability performance reports. | once completed, send to upload on our DMC sustainability section of the website. | Sustainability Team | Demonstrate transparency in sustainability performance. |  | 2026-12-01
7 |  | 7. Create a staff sustainability training course. | from the training modules of Travelife, determine and create sustainability points for training for each business department. | Sustainability Team | Build staff capacity in sustainability practices. |  | 2025-12-01
8 |  | 8. Complete and maintain Sustainability Monitoring & Evaluation spreadsheet. | review each week for to ensure regular input of data. Follow-up. | Sustainability Team, Building Management | Maintain accurate sustainability monitoring. | 2025-03-01 | 2025-12-25 |  |  |  | Ongoing process; ensure completeness and correctness.
9 | Internal Management: Social Policy and Human Rights | 1. Review and update employment contracts in accordance with local labor laws. | HR to check with Ministry of Manpower for updates in HR/Labor law legislation. Update employments contracts accordingly | HR Manager | Uphold fair treatment and align with human rights standards for all employees. | 2025-01-01 | 2025-12-01 |  |  |  | Compliance with Egyptian Labor Law.
10 |  | 2. Create and distribute a disciplinary procedure to all staff. | HR to check with Ministry of Manpower and updates in HR/Labor law legislation. Update current policy, add any legal references and distribute after senior management approval. | HR Manager | Ensure clear disciplinary procedures for employees. | 2025-01-01 | 2025-06-01
11 | Internal Environmental Management | 1. Install energy-efficient lighting and appliances. | Check the market options and assess, replace as necessary. | Facilities Management / Finance | Reduce energy consumption by 15% by 2026. | 2025-01-01 | 2025-12-01 |  |  |  | Equipment and installation costs.
12 |  | 2. Implement water-saving technologies in office spaces. | add signage to all kitchens/toilets/Cleaning about water practises | Facilities Management / Finance | Reduce water consumption by 15% by 2026. | 2025-03-01 | 2026-06-01
13 |  | 3. Promote a paperless culture. | go digital where possible, avoid printing out unnecessarily. | Office management | Reduce paper usage by 30% by 2026. | 2025-03-01 | 2026-12-01
14 |  | 4. Use recycled paper for all paper usage and client info. | keep up to date on sustainable options, ensure only recycled paper is purchased. | Facilities Management / Finance |  | 2025-03-01 | 2026-03-01
15 |  | 5. Minimize single-use plastics and encourage reusable alternatives. | buy in bulk to reduce several containers. Provide filter drinking water from main supply. Staff to use own cups no plastic. Reusable cutlery supplied in all kitchens. | Facilities Management / Finance | Reduce single-use plastics in office usage. | 2024-08-01 | 2025-12-01 | Complete
16 |  | 6. Bulk purchase to reduce deliveries. | Review purchasing + delivery options | Facilities Management / Finance | Reduce carbon footprint from procurement. |  | 2026-01-01
17 |  | 7. Create a sustainability procurement directive. | create an overview of all internal procurements and identify sustainable options. Issue directives to procurement personnel. | Sustainability Management / Procurement | Integrate sustainability into procurement decisions. |  | 2025-06-01
18 |  | 8. Calculate carbon emissions using the CARBON CALCULATIONS Policy. | create a Carbon emissions monitoring form, calculate and offset - Market research into carbon offsetting programs. | Sustainability Management | Compensate for office carbon emissions. | 2025-03-01 | 2026-01-01
19 |  | 9. Review all current purchases and storage of chemicals. | Search for suppliers providing sustainable cleaning products, ensure all current product storage meets company and sustainability goals. | Purchasing / building Maintenance / Cleaning | Minimize use of harmful substances. | 2025-03-01 | 2025-12-01
20 | Transportation | 1. Encourage public transport use and implement vehicle sharing. | Review staff vehicle use, look into alternatives that minimise carbon emissions. | Operations Manager + Commercial Director | Reduce CO2 emissions from company-related transport by 20% by 2027. |  | 2027-12-01 |  |  |  | Investment in vehicle upgrades and carbon offset programs.
21 |  | 2. Transition to fuel-efficient or electric vehicles for tours and transfers. | look into alternative transport options. | Operations Management |  | 2025-01-01 | 2027-12-01 |  |  |  | Investment in vehicle upgrades and carbon offset programs.
22 | Accommodations | 1. Ascertain which hotels are already certified and encourage others to get certified. | keep sending out reminders and update the HOTELS -Sustainable certification spreadsheet. | Contracting & Product Management | Achieve full sustainability compliance among partnered hotels. | 2024-09-01 | 2026-12-01
23 | Excursions and Activities | 2. Conduct a full review of all excursions and identify sustainability training needs for suppliers. | Sustainability green team, Quality and Ops to conduct sustainability meetings with all suppliers to identitfy current compliance, improvements and any additional training needs. | Operations, Destination and Quality Mgrs | Minimize negative impacts and maximize positive impacts on destinations. | 2025-06-01 | 2026-06-01 |  |  |  | Check and assist excursions not meeting sustainability goals.
24 |  | 3. Train tour guides on sustainable tourism practices. | Determine Sustainability training needed and ensure all REPS/GUIDES have received the codes of conduct and best practice for all excursion types. Sustainability training needs to be added to compulsory training subjects. | Training Dept., HR, Operations, Destination and Quality Mgrs | Raise awareness, minimize negative impacts and maximise positive impacts. | 2025-03-01 | 2026-02-01
25 |  | 4. Develop and promote eco-friendly tour packages. | search for existing eco-friendly suppliers (eco-lodge's etc) check what activities/excursions could be developed. Check existing portfolio to check if any can be adapted to meet requirements. | Operations, Destination and Quality Mgrs | Encourage customers to seek out and participate in sustainable excursions. Raise Awareness. Promote sustainable behaviours in our supply chain. | 2025-08-01 | 2027-06-01
26 |  | 5. Reduce paper use for welcome meeting letters/packs. | Check for ways to reduce welcome letter paper usage. Brainstorm with all relevant departments. Look into new ways to convey information. | Operations / IT | Reduce paper usage for welcome materials. |  | 2025-12-01
27 |  | 6. Distribute codes of conduct to suppliers and include in REP packs. | Ensure all suppliers have received the correct codes of conduct / best practise and add to REP training. | Sustainability / Training / Ops | Ensure excursion suppliers comply with sustainability codes. | 2025-03-01 | 2025-06-01
28 |  | 7. Collaborate with sustainable excursion suppliers to sponsor a sustainability guideline. | Discuss with existing sustainable suppliers possibilities to Sponsor sustainability guide, we can go to HEPCA, the CDWS etc or maybe incorporate into a destination QR code and show to guests at welcome meetings. Brainstorm. | Sustainability Coordinator / Ops / Quality | Promote awareness of sustainable providers and practises.. | 2025-06-01 | 2026-01-01
29 | Waste Management | 1. Introduce office recycling and shredding. | Purchase a shredder, allocate in relevant resort offices, distribute guidelines re shredding, recycling. Research recycling options in Hurghada. | HR Manager, building management | Achieve a 50% reduction in office waste by 2027. | 2025-02-01 | 2027-12-01 |  |  |  | Waste management systems, training.
30 |  | 2. Minimize single-use plastics and encourage reusable alternatives. | Monitor all dept's and operations areas: office, transport etc. make a list of all possible uses of single-use plastics and advise solutions to reduce or replace. | Facilities Management / Ops | minimise single use plastics in our regular operations. | 2025-05-01 | 2027-08-01
31 |  | 3. Educate staff on waste reduction practices. | Distribute Masters waste reduction guides to all employees. | Sustainability Coordinator | staff awareness and compliance | 2025-07-01 | 2027-12-01
32 | Internal Energy Management | 1. Explore battery alternatives and transition from diesel generators. | check market options and advise costs of any better sustainable options. | Facilities Management | Improve energy efficiency. | 2025-06-01 | 2026-01-01
33 |  | 2. Explore options for battery alternatives - office usage | research costs for rechargable batteries. | Facilities Management | Replace single-use batteries with rechargeable options. | 2025-03-01 | 2025-07-01
34 | Donations | 1. Contact NGO (HEPCA) to donate or Volunteer. | Contact any local NGO's to see what projects, activities we can contribute, donate to or volunteer to help - ie. Clean-up environment days etc. display and distribute to employees. | Sustainability Team | Support sustainability initiatives through donations or volunteering. | 2025-06-01 | 2025-12-25 |  |  |  | HEPCA is probably best due to similar interests (sea-trips/diving etc)